## Instructions
HEXIS — EU AI Act Compliance Roadmap
EU AI Act Compliance Starter Kit · Template #4 of 4
PURPOSE
This template transforms your compliance gap analysis into an actionable roadmap with milestones, owners, and deadlines. It provides a structured path from current state to full compliance.
PREREQUISITE TEMPLATES
1. AI System Inventory — identifies your AI systems (Template #1)
2. Risk Classification Worksheet — determines risk level per system (Template #2)
3. EU AI Act Compliance Assessment — identifies compliance gaps (Template #3)
Use those results to populate this roadmap.
HOW TO USE
Step 1: Transfer Non-Compliant and Partially Compliant items from the Assessment (Template #3) into the Roadmap sheet.
Step 2: Break each gap into specific actions with clear deliverables.
Step 3: Assign owners, set target dates aligned with EU AI Act deadlines, and estimate effort.
Step 4: Use the Timeline View to visualise your compliance journey month by month.
Step 5: Track progress on the Dashboard. Update status as actions are completed.
COMPLIANCE PHASES (SUGGESTED)
Phase 1 — Foundation (Months 1-3): Governance structure, risk management framework, AI literacy.
Phase 2 — Documentation (Months 3-6): Technical documentation, data governance, logging setup.
Phase 3 — Implementation (Months 6-9): Human oversight, accuracy/robustness, transparency.
Phase 4 — Validation (Months 9-12): Conformity assessment, FRIA, EU database registration.
Phase 5 — Maintenance (Ongoing): Post-market monitoring, incident reporting, periodic review.
ACTION STATUS DEFINITIONS
Not Started — Action has not been initiated.
In Progress — Work is underway but not yet complete.
Blocked — Action is blocked by a dependency or external factor.
Completed — Action is finished and evidence is documented.
Deferred — Action postponed with documented justification.
SYSTEM ID CONVENTION
Use 'ALL' as System ID for organisation-wide obligations that apply across all systems (e.g., AI Literacy, Post-Market Monitoring). Use specific IDs (AI-001, AI-002) for system-specific actions.
If a system falls under multiple Annex III areas, create separate action rows per obligation area.
ORIENT FRAMEWORK ALIGNMENT
HEXIS ORIENT: Observe (inventory) → Risk (classify) → Identify (map obligations) → Evaluate (assess gaps) → Navigate (plan actions) → Track (monitor).
This template maps to the Navigate and Track stages.
KEY DEADLINES REMINDER
Already in force: Prohibited practices (Art. 5) + AI literacy (Art. 4) — since 2 Feb 2025.
Already in force: GPAI obligations (Chapter V) — since 2 Aug 2025.
Upcoming: High-risk systems, Annex III — 2 Aug 2026.
Upcoming: High-risk systems, Annex I (product safety) — 2 Aug 2027.
Proposed: Digital Omnibus may extend deadlines if adopted — monitor status.
LEGAL DISCLAIMER
This template provides a structured planning framework. It does not constitute legal advice. Consult qualified legal counsel for compliance determinations.
hexis.center · EU AI Act Compliance Starter Kit · v1.0

## Roadmap
Action ID | System ID | Obligation Area | EU AI Act Article | Compliance Phase | Action Description | Deliverable | Owner | Status | Priority | Start Date | Target Date | Completion Date | Effort (Person-Days) | Dependencies | Notes / Evidence
ACT-001 | ALL | AI Literacy & Training | Art. 4 | Phase 1 — Foundation | Develop AI literacy training programme for all staff involved with AI systems. | AI Literacy Training Programme + assessment criteria | L&D Team | In Progress | Critical | 2026-03-01 | 2026-05-15 |  | 15 |  | Art. 4 already in force since 2 Feb 2025. Priority remediation.
ACT-002 | AI-001 | Risk Management System | Art. 9 | Phase 1 — Foundation | Complete lifecycle risk assessment and update risk register to cover all stages per Art. 9. | Updated Risk Register v3.0 with lifecycle coverage | DPO Team | Not Started | High | 2026-04-01 | 2026-06-30 |  | 20 |  | Current register v2.1 missing residual risk assessment and lifecycle stages
ACT-003 | AI-001 | Data Governance | Art. 10 | Phase 1 — Foundation | Establish data governance framework for training data. Implement bias testing protocol. | Data Governance Policy + Bias Testing Report | Data Team | Not Started | Critical | 2026-03-15 | 2026-05-30 |  | 25 |  | No existing data governance. Requires new framework from scratch.
ACT-004 | AI-001 | Technical Documentation | Art. 11 | Phase 2 — Documentation | Restructure system documentation to meet Art. 11 and Annex IV requirements. | Technical Documentation Package (Annex IV compliant) | Engineering | Not Started | High | 2026-05-01 | 2026-07-15 |  | 30 | ACT-002, ACT-003 | Depends on risk register and data governance being in place.
ACT-005 | AI-001 | Record-Keeping & Logging | Art. 12 | Phase 2 — Documentation | Implement automatic logging system. Define log retention policy and audit trail. | Logging System + Retention Policy Document | Engineering | Not Started | Medium | 2026-05-15 | 2026-07-31 |  | 15 | ACT-004 | Logging specs to be derived from technical documentation.
ACT-006 | AI-002 | Transparency Disclosure | Art. 50 | Phase 3 — Implementation | Enhance chatbot AI disclosure mechanism. Add content labelling for AI-generated responses. | Enhanced disclosure UI + content labels | Product Team | Completed | Low | 2026-01-15 | 2026-03-01 | 2026-02-28 | 5 |  | Completed ahead of schedule. Disclosure visible at conversation start.
ACT-007 | AI-003 | Conformity Assessment | Art. 43 | Phase 3 — Implementation | Initiate internal conformity assessment procedure for credit scoring system. | Conformity Assessment Report + CE Declaration | Compliance | Not Started | Critical | 2026-06-01 | 2026-08-01 |  | 40 | ACT-002 | Credit scoring = Annex III §5(b) high-risk. Internal assessment sufficient (not biometric).
ACT-008 | AI-001 | EU Database Registration | Art. 49 | Phase 4 — Validation | Register TalentAI HR Screening in EU database before deployment. | EU Database Registration Confirmation | Compliance | Not Started | High | 2026-07-01 | 2026-07-31 |  | 3 | ACT-004, ACT-007 | Registration requires conformity assessment to be complete.
ACT-009 | ALL | Post-Market Monitoring | Art. 72 | Phase 5 — Maintenance | Establish post-market monitoring system for all high-risk AI systems. | Post-Market Monitoring Plan + quarterly review schedule | Risk Team | Not Started | Medium | 2026-07-15 | 2026-09-30 |  | 10 | ACT-002 | Proportionate to risk. Include feedback loops and incident triggers.
ACT-010 | ALL | Serious Incident Reporting | Art. 73 | Phase 5 — Maintenance | Define incident reporting procedure and designate responsible contact for authority reporting. | Incident Reporting SOP + authority contact details | Compliance | Not Started | High | 2026-06-01 | 2026-07-31 |  | 5 |  | Tiered deadlines: 15 days (standard), 10 days (death), 2 days (critical infrastructure). Define thresholds and escalation path.

## Timeline View
Action ID | Action Description | Owner | Status | Mar 2026 | Apr 2026 | May 2026 | Jun 2026 | Jul 2026 | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026 | Jan 2027 | Feb 2027
| EU AI Act Annex III deadline: 2 Aug 2026 | [7 empty] | ⚑ DEADLINE
ACT-001 | AI Literacy Training Programme | L&D Team | In Progress | ▬ | ▬ | ▬
ACT-002 | Complete Risk Register v3.0 | DPO Team | Not Started |  | ▬ | ▬ | ▬
ACT-003 | Data Governance Framework | Data Team | Not Started | ▬ | ▬ | ▬
ACT-004 | Technical Documentation (Annex IV) | Engineering | Not Started |  |  | ▬ | ▬ | ▬
ACT-005 | Logging System + Retention Policy | Engineering | Not Started |  |  | ▬ | ▬ | ▬
ACT-006 | Chatbot Transparency Disclosure | Product Team | Completed | [10 empty] | ▬ | ▬
ACT-007 | Conformity Assessment (Credit Scoring) | Compliance | Not Started |  |  |  | ▬ | ▬ | ▬
ACT-008 | EU Database Registration | Compliance | Not Started |  |  |  |  | ▬
ACT-009 | Post-Market Monitoring Plan | Risk Team | Not Started |  |  |  |  | ▬ | ▬ | ▬
ACT-010 | Incident Reporting SOP | Compliance | Not Started |  |  |  | ▬ | ▬

## Dashboard
Compliance Roadmap — Dashboard
OVERALL PROGRESS
Total Actions
Completed
In Progress
Not Started
Blocked
Deferred
Completion Rate
In Progress Rate
PRIORITY BREAKDOWN
Critical Actions
High Actions
Medium Actions
Low Actions
PHASE PROGRESS
Phase | Total | Completed | In Progress | Not Started | % Complete
Phase 1 — Foundation
Phase 2 — Documentation
Phase 3 — Implementation
Phase 4 — Validation
Phase 5 — Maintenance
EFFORT SUMMARY
Total Estimated Effort (Person-Days)
Effort Completed
Effort Remaining
Average Effort per Action
DEADLINE RISK ASSESSMENT
Actions due before 2 Aug 2026 (Annex III deadline)
Overdue actions (target date < today)
Blocked actions requiring attention
hexis.center · EU AI Act Compliance Starter Kit · Regulation (EU) 2024/1689